## Vijaya Kumar
Project Plan & Status
Date | Project | Task Assigned | Duration | Status | Remarks | Plan for tomorrow | Status Responsible Person
2019-03-19 | Aatralz | Certification page and home page design with theme | 4 hours | In Progress | - | iStop tracker and PR | Thenmozhi
| iStop | Masters | 3 hours | In Progress | -
2019-03-20 | Aatralz |  | 2 hours | Completed | - | iStop and PR | Aravin
| iStop |  | 4 hours | In Progress | -
| PR |  | 3 hours | In Progress | -
2019-03-21 | PR | Bug fix, Cost Center, Project, | 2 hours | Completed | - | iStop and PR | Alexandar
|  | View page | 2 hours | In Progress | -
| iStop | KT to Hema and Keerthika | 1 hours | Completed | -
2019-03-22 | iStop | Integration, Fixed Dynamic Sidebar,Fixed DropDown Values and Table Corrections | 6 hours | Completed | - | iStop and PR | Keerthika
| PR | Indent View page , Calculation part for estimate cost and aligned cost, delegate screen, | 7 hours | Completed
2019-03-23 | iStop | Remove pass the url in parameter,file upload functionality and made api changes | 3 1/2 hours | Completed | - | iStop and PR | Hema
| ertino | Setup the server | 1 hours
| Aatralz | Correct the issue | 1/2 hours
2019-03-25 | iStop | Date picker bug fixe,API update | 3 hours | Completed | - | iStop and PR | S.Mayandi
| Disc | Process video bug | 4 hours
2019-03-26 | Ertino | Ertino bug fix | 8hours | In Progress | - | Aatralz | Keerthika

## Aravin
Project Plan & Status
Date | Project | Task Assigned | Duration | Status | Remarks | Plan for tomorrow | Status Responsible Person
19-03-2019 | DISC | Bug fixing | 1 hours | In Progress | - | Forms portal , ISPR | Thenmozhi
| ISPR | Bug fixing | 1 hours | In Progress | -
| iStop | Responsible UI | 1 hours | In Progress | -
| Aatralz | UI issue | 1 hours | In Progress | -
2019-03-20 | Forms portal | Functionality fix | 6.5 hours | In Progress | - | Daimler | Aravin
2019-03-21 | Daimler | [5 empty] | Alexandar
2019-03-22 | Daimler | [5 empty] | Keerthika
2019-03-23 | Ibill | deployment | 1 hours | completed | _ | form portal and disc | Hema
| Disc | Fix the bug and intergration | 4 hours | completed | _
| Forms portal | retro fitment form | 1 hours | completed | _
2019-03-25 | iStop | Date picker bug fixed | 1/2 hour | completed | - | Forms | S.Mayandi
| Disc | Fixed the bug ,Performance->ebse Integration, | 3 and 1/2 hours | completed | -
| Disc | PDP changes+PDP |  | In Progress | -
2019-03-26 | DISC | PMP , PDP , Deploy error - Bug fix | 8 hours | completed | - | iStop - Daimler deployment | Thenmozhi
2019-03-27 | Daimler | [5 empty] | Alexandar
2019-03-28 | Daimler | [5 empty] | Keerthika

## Alexander
Project Plan & Status
Date | Project | Task Assigned | Duration | Status | Remarks | Plan for tomorrow | Status Responsible Person
2019-03-19 | Forms | Submit form Modal | 2 hours | Complete | Laptop Slow | Finance form Validation | Thenmozhi
| Finanace form | Form Design | 2.5 hours | In Progress | Laptop Slow
| Integration learning | Learning | 1 hour | In Progress | -
2019-03-20 | Finance form | Validation | 6 hours | Complete | - | Remaining form design | Aravin
2019-03-21 | Finas ID Generation Forms | Preview method add | 2 hours | Complete | - | New Upload page design | Alexandar
| MES Showcase | Login and Main Page Design | 4 hours | Complete | -
|  | New Upload Page Design | 1 hours | In Progress | -
2019-03-22 | MES ShowCase | drag & drop fixed in upload pages | 6 hours | Complete | - | Forms correction and MES design correction | Keerthika
|  | and responsive fixed |  |  | -
2019-03-23 | MES Showcase | Index page | 7 hours | Complete | - | pdf viewer | Hema
2019-03-25 | MES PDF viewer | Learning | 7 hours | In Progress | - | pdf viewer | S.Mayandi
2019-03-26 | MES PDF viewer | Full screen Error fix | 7 hours | In Progress | - | Service Measure Portal | Thenmozhi
2019-03-27 | Service Measure Portal | Vehicle information Page | 6 hours | Complete | - | Service Measure Portal | Alexandar
|  | Component creation | 1 hour
2019-03-28 | Service Measure Portal | Part Information and cost information page | 2 hours | Complete | - | Service Measure Portal | Keerthika

## Mayandi
Project Plan & Status
Date | Project | Task Assigned | Duration | Status | Remarks | Plan for tomorrow | Status Responsible Person
19-03-2019 | Java Learning | Configuration Modal, Maven project creation | 6 hours | In progress | - | Java learning | Thenmozhi
2019-03-20 | Java Learning | Abstract, collections, maps,interface | 7 hours | In progress | - | Java learning | Aravin
2019-03-21 | Java Learning | Tables - Format cell content, Table Border, Adding Image, Tables list, Image rorate, scaling, Change position | 7 hours | In progress | - | Java learning | Alexandar
2019-03-22 | Java Learning | Java installation , PDF design - 20% | 6 hours | In progress | - | PDF design | Keerthika
2019-03-23 | Ispr | ispr pdf forms | 7 hours | In progress | - | PDF design | Hema
2019-03-25 | Ispr | ispr pdf forms | 7 hours | In progress | - | PDF design | S.Mayandi
2019-03-26 | Java Learning | Excel read,Write and Hypernet (ORM) learning | 7 hours | In progress | - | Hypernet learning | Thenmozhi
2019-03-27 | Java Learning | MVC - Spring - Created Rest API | 7 hours | In progress | - | MVC - Spring - Created Rest API | Alexandar
2019-03-28 | java learning | Spring - Rest controller | 7 hours | completed | - | Hypernet learning | Keerthika

## Keerthika
Project Plan & Status
Date | Project | Task Assigned | Duration | Status | Remarks | Plan for tomorrow | Status Responsible Person
19-03-2019 | Component creation | Check box creation | 2 hours | In Progress | - | Bus ISFM portal | Thenmozhi
| iStop | Responsive screens | 3 hours | Completed
| PMP | Dashboard changes | 1 hours | Completed
2019-03-20 | Boostrap 4 | learning | 2 hours | In Progress | - | ESFM - POC | Aravin
| DISC | Bug fix | 3 hours | Completed
| Aatralz | Helping hema | 30 mins | Completed
| PR | Masters page | 30 mins | Completed
2019-03-21 | Aatralz | Skill block page | 4 hours | Completed | - | Istop | Alexandar
| iStop | KT from Vijay kumar | 1 hours | Completed
2019-03-22 | iStop | Learning API Integration and Sidebar Fixed | 6 hours | In Progress | - | Will assign by Vijayakumar | Keerthika
2019-03-23 | Component creation | creation html,css and js files | 1 hours | Completed | - | bus hr | Hema
| iStop | intergration | 3 1/2 hours | Completed
| iStop | fix the bug ui | 2 hours | In Progress
2019-03-25 | iStop | Bug fixed | 3Hours | Completed | - | Ertino | S.Mayandi
| Bus Hr | Login page,Course list page, model page | 4 hours
2019-03-26 | Ertino - website | Ertino website in Wordpress | 4 hours | - | - | Ertino website in HTML | Thenmozhi
|  | Ertino website in HTML | 4 hours | In Progress
2019-03-27 | Ertino - website | Ertino website in HTML | 5 hours | In Progress | - | Ertino website in HTML | Alexandar
| Component module | Module creation for Alexander | 1 hours | Completed
2019-03-28 | Bus-hr | designed course list page and responsive fix | 7 hours | Completed | - | Will assign by Yogan | Keerthika

## Hema
Project Plan & Status
Date | Project | Task Assigned | Duration | Status | Remarks | Plan for tomorrow | Status Responsible Person
19-03-2019 | Component creation | Check box creation | 2 hours | In Progress | - | Aatralz | Thenmozhi
| iStop | Responsive screens | 40 mins | Completed | -
| Aatralz | Home page | 4 hours | In Progress | -
2019-03-20 | Aatralz | Home page | 1 hours | Completed | - | Aatralz | Aravin
| Aatralz | Course page | 5 hours | In Progress | -
2019-03-21 | Aatralz | Certification page | 7 hours | In Progress | - | Aatralz | Alexandar
2019-03-22 | Aatralz | Operations in skill blog page and light page design correction | 7 hours | In Progress | - | Will assign by Vijayakumar | Keerthika
2019-03-22 | Aatralz | skill blog | 1 hours | Completed | - | Aatralz | Hema
|  | Certification page | 6 hours | In Progress
2019-03-25 | Aatralz | Bug fix | 7hours | In Progress | - | Ertino | S.Mayandi
2019-03-26 | Aatralz | Registration form creation and Modal creation | 4hours | Completed | - | Will assign by Yogan | Thenmozhi
| Component creation | Nav bar creation | 4hours | In Progress
2019-03-27 | Aatralz | Responsive fix | 1hours | Completed | - | Will assign by Yogan | Alexandar
| i-Stop | UI Bug Fix | 5 hours | In Progress
2019-03-28 | Aatralz | Correction and file merge | 5 hours | Completed | - | Will assign by Yogan | Keerthika
| Component creation | Nav bar creation | 2 hours | Completed

## Thenmozhi
Project Plan & Status
Date | Project | Task Assigned | Duration | Status | Remarks | Plan for tomorrow | Status Responsible Person
19-03-2019 | DISC | PMP Test plan documentation | 3 hours | Completed | - | PR Documentation | Thenmozhi
|  | PDP Test plan documentation | 2 hours | Completed | -
|  | ISPR Test plan documentation | 1 hours | In Progress | -
|  | BUGS | 1 hours | In Progress | -
2019-03-20 | DISC | ISPR Test plan documentation | 3 hours | Completed | - | PR Documentation | Aravin
|  | BUGS | 1 hours | Completed | -
| PR | Test plan Documentation | 4 hours | In Progress | -
2019-03-21 | PR | Test plan Documentation | 7 hours | In Progress | - | Disc user manual | Alexandar
2019-03-22 | PR | Test plan Documentation | 5 hours | Completed | - | Disc user manual | Keerthika
| DISC Bugs | Discussed with aravin and verified the pending bugs | 1 hours | Completed | -
2019-03-23 | Pr | documentation changes | 2 hours | In Progress | _ | pr and disc | Hema
| Disc | user manual | 1 hours | In Progress
| istop,pdp,ertino | fix the ebug | 4 hours | In Progress
2019-03-25 | Disc | Supplier login issue | 1 hour | Completed | - | Disc | S.Mayandi
|  | Testing process, PDP,PMP | 5hours | Completed
|  | Meeting with Rajkumar | 1hour | Completed
2019-03-26 | DISC | PDP and PMP Bugs reporting | 8hours | In Progress | - | iStop | Thenmozhi
2019-03-27 | i-Stop | i-Stop bugs reporting | 7hours | In Progress | - | iStop | Alexandar
| Disc Portal | Explanation given to SATHEESH about User previleges and Process module for user documentation | 1hours | Completed
2019-03-28 | Ertino | Ertino bug discussion with vijay | 5hours | Completed | - | iStop | Keerthika
| Packaging portal | File upload issue | 2hours | Completed